## Sheet1
Risk Name | Likelihood of risk. 10 definitately happening; 0 never going to happen | Impact of Risk. 10 unable to complete project, 0 no impact on project | Risk Score (Likelihood x Impact) | Risk management strategy (accept/avoid/mitigate) | Actions to mitigate/avoid risk
Unable to take samples | 10 | 10 | 100 | Accept | None possible in current time frame
Unable to attend conference | 10 | 5 | 50 | Mitigate | Look for another conference or request funding to attend conference after PhD is finished
No access to data | 3 | 9 | 27 | Avoid | Ensure that data access is possible remotely and have access to correct software