## Sheet1
Risk | Likelihood* | Impact** | Score† | Management Strategy†† and Actions
Unable to take samples | 10 | 10 | 100 | Accept | None possible in current time frame
Unable to attend conference | 10 | 5 | 50 | Mitigate | Look for another conference or request funding to attend conference after PhD is finished
No access to data | 3 | 9 | 27 | Avoid | Ensure that data access is possible remotely and have access to correct software
* 10: definitely happening - 0: never going to happen
**10: unable to complete project - 0: no impact on project
†(Likelihood x Impact)
†† accept/avoid/mitgate